## Gantt Chart
PRISM: Poverty Risk Identification through Statistical Mapping
Explainable Machine Learning Framework for District-Level Poverty and Development Risk Assessment in India
Team | Amish Kapoor ¦ Aryan Chaturvedi ¦ Kushal |  |  | Today | 2026-09-16 |  | Schedule | 2026-08-17 | 2026-11-20
TASK | ASSIGNED TO | PROGRESS | START | END | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20
Phase 1: Requirements, Proposal & System Design
Project Proposal & Problem Definition | Kushal | 100 | 2026-08-17 | 2026-08-20
System Architecture & Workflow Design | Aryan | 100 | 2026-08-18 | 2026-08-22
Use Case Diagram & ER Diagram | Kushal | 100 | 2026-08-21 | 2026-08-27
Project Documentation & Technical Specification | Amish | 100 | 2026-08-23 | 2026-08-29
Phase 2: Dataset Collection & Data Integration
Census 2011 Dataset Preparation | Amish | 100 | 2026-08-24 | 2026-08-30
NFHS-5 Data Transformation & Preparation | Aryan | 100 | 2026-08-26 | 2026-09-03
MPI & Aspirational Districts Data Preparation | Kushal | 100 | 2026-08-28 | 2026-09-04
District Key Creation & Dataset Merging | Aryan | 100 | 2026-09-01 | 2026-09-10
Data Validation & Merge Verification | Amish | 100 | 2026-09-08 | 2026-09-15
Phase 3: EDA, Cleaning & Feature Engineering
Exploratory Data Analysis & Missing-Value Study | Kushal | 55 | 2026-09-10 | 2026-09-19
Outlier Analysis & Data Cleaning | Amish | 0 | 2026-09-16 | 2026-09-25
Feature Engineering & Rate Conversion | Aryan | 0 | 2026-09-20 | 2026-09-29
Feature Selection & Correlation Pruning | Kushal | 0 | 2026-09-26 | 2026-10-03
Phase 4: Machine Learning Modeling
Feature Scaling & Clustering Dataset Preparation | Aryan | 0 | 2026-09-30 | 2026-10-05
K-Means & Hierarchical Clustering | Amish | 0 | 2026-10-04 | 2026-10-12
Clustering Evaluation & Cluster Interpretation | Kushal | 0 | 2026-10-10 | 2026-10-16
Classification Model Training: LogReg, RF & SVM | Aryan | 0 | 2026-10-13 | 2026-10-22
Hyperparameter Tuning & Cross-Validation | Amish | 0 | 2026-10-20 | 2026-10-28
Phase 5: Evaluation, Explainability & Validation
Model Evaluation: Precision, Recall, F1 & Confusion Matrix | Kushal | 0 | 2026-10-25 | 2026-11-02
Feature Importance & Explainability Analysis | Aryan | 0 | 2026-10-30 | 2026-11-06
Validation Against Aspirational Districts List | Amish | 0 | 2026-11-03 | 2026-11-09
Robustness & Reproducibility Testing | Kushal | 0 | 2026-11-07 | 2026-11-12
Phase 6: Dashboard, Documentation & Final Delivery
Visualization & District-Level Results Dashboard | Aryan | 0 | 2026-11-08 | 2026-11-14
Final Report, Results & Limitations | Amish | 0 | 2026-11-10 | 2026-11-17
Final Presentation, Viva & Project Demonstration | Kushal | 0 | 2026-11-14 | 2026-11-20